## Sheet1
Sprint 1 (Planning) | Sprint 2 (Development) | Sprint 3 (Integration & Testing) | Sprint 3 (Bug Sprint)
Product Backlog | Product Backlog | Product Backlog | Product Backlog
1) Basic Understanding of AWS Platform | 1) Create Initial website using HTML and CSS - Travel Application | 1) Discuss with Flight Service,Railway Service & Taxi Service Team | 1) Front End Development for Flight Service, Railway Service, Taxi Service , Accomodation Service
2) Explore AWS Platform | 2) Setup php server for further development with Travel Application | 2) Integration of APIs with Travel Application | 2) Resolve Persitent/Old Bugs
3) Explore different Travel Application (Internet) | 3) Host Initial Website developed in AWS Platform | 3) Testing of APIs | Sprint Backlog
4) Plan Input Parameters Required for our Travel Application | 4) Develop Initial User Inferface (Registration and Login) | 4) Resolve issues Bugs after Integration | 1) Front End Development for Flight Service
5) Plan & Initial Setup of AWS Platform (EC2 Instance) for Hosting our Travel Application | 5) Store User Credentials and Data in MySQL | 5) Hosting Website in AWS | 2) Front End Development for Railway Service
6) Explore different servers (Apache,XAMAPP) & SQL database Required for our Website | 6) Disscussion with Teams to be in line with product Integration & Specification | Sprint Backlog | 3) Front End Development for Taxi Service
7) Initial Outlay of Travel Application using (HTML & CSS, or C# .Net FrameWork) | Sprint Backlog | 1) Discussion with Flight Service & Railway Service Team | 4) Front End Development for Accomodation Service
8) Discuss with Teams to understand product requirement & Understand their Specification | 1) Develop Initial Website using HTML& CSS using VS Code | 2) Understand RESTful APIs Developed by Flight Service Team | 5) Resolve Bugs
Sprint Backlog | 2) PHP Server Creation using Apache Server | 3) Understand RESTful APIs Developed by Railway Service Team | 6) Buffer Tasks
1) Kickstart -> Create AWS Account (Student Account ) | 3) Hosting Initial Website in AWS Platform (Initial Website interface) | 4) Understand RESTful APIs Developed by Taxi Service Team | Sprint Review
2) Create an Instance (EC2 Instance) | 4) Develop Registration Form, Login Page & UserInterface | 5) Understand RESTful APIs Developed by Accomodation Service Team
3) Use Azure Portal to Create a basic Web Application (Since it is Familiar Platform) | 5) Test registration form, Login Page & User Interface | 6) Understand RESTful APIs Developed by Payment Team
4) Host Web Application Created using Visual Studio (C# or .NET Framework) | 6) Store User Credential and User Data in Database | 7) Integrate RESTful API Developed by Flight Service Team
5) Implement input Parameters required for Travel Web Application | 7) Discusss with any one of the cross connected Teams and basic integrate their platform | 8) Integrate RESTful APIs Developed by Railway Service Team | Retrospective
6) DataBase Setup for storing User Parameters | Sprint Review | 9) Integrate RESTful APIs Developed by Taxi Service Team | 1) Unable to Contact Taxi, Accomodation & Payment Teams and Understand/Gather Information
Sprint Review | 1) Developed Initial Website using HTML & CSS | 10 Integrate RESTful APIs Developed by Accomodation Service Team
1) Created AWS Account and understand AWS Platform | 2) Host Inistial website in AWS Platform | 11) Integrate RESTful APIs Developed by Payment Team
2) Able to capture Input Parameters Required for Our Travel Application | 3) Developed Registration form, Login Page & UserInterface | 12) Test Integrated API - Flight Service
3) Created EC2 instance in AWS and host a demo website using EC2 Instance | 4) Test Registration form, Login Page & User Interface | 13) Test Integrated API - Railway Service
4) Create a web Application using C# & .NET Framework and host using Azure | 5) Stored User Credential & User Data In Database | 14) Test Integrated API - Taxi Service
5) DataBase Setup for Storing Input Parameters | Retrospective | 15) Test Integrated API - Accomodation Service
6) Discussed with Other Teams to Understand Product Requirement & Specifiation | 1) Delay in Interaction with Team for understanding Basic integration and Parameter | 16) Test Integrated API - Payment Service
Retrospective |  | 17) Test Integrated All Service After Integration - Travel App
1) Team was able to develop a basic web application using C# .NET Framework, but could foresee future risks and Incompatibality Issues if Product is developed using C# & .NET Framework (Discussed with Professor And Team mates and Come up with backup Plans) | 2) Delay in start of Sprint 2 Development as Team was working around with a Plan which foresaw future risk and compatibility Issue | Sprint Review
2) Team was able to host a basic web application in AWS Platform using static,eventually the team worked around to make the web application host dynamically. | 3) Moved Few Tasks related to Server and Integration Testing to Sprint 3 to avoid delay in Time Line | 1) Discussion with Flight Service & Railway Service Team
2) Understand RESTful APIs Developed by Flight Service Team
3) Understand RESTful APIs Developed by Railway Service Team
Retrospective
1) Blocker - With Taxi Service, Accomodation Service & Payment Service
2) Front end Development with Respect to Different Services Offered (Under Estimation)